## CoS Tracker
189 KENT STREET (SALUS PLACE) CONTRACT OF SALE TRACKER | [16 empty] | Bespoke Lots | 11
[24 empty] | COS | Gurner Framework |  |  | Gurner Framework |  | Gurner Framework | Gurner Framework | COS | Gurner Framework | Gurner Framework | COS | Gurner Framework | COS | COS | Gurner Framework | Gurner Framework | COS
[19 empty] | Includes: Motirized Window Furnishings Depreciation Schedule Inc. Interest on Deposit |  |  |  |  | The purchaser must submit a written brief outlining requested bespoke changes within the contractual timeframe, triggering the bespoke design process. | Design team prepares sketch plan. Buildability reviewed by GURNER team. No dimensions on sketch plan. If dimensioned plans are provided, Gurner disclaimer must be added to plans. Responsible: Design Team + Customisations Manager | 01. Preliminary cost ranges provided by Quantity Surveyor (QS or GURNER) as per table 6.2 in Customisations Framework 02. Updated $20k consultant & Gurner allowance reported 03. Layout initialled Produce letter: Customisations Manager Review of letter: Development Manager Responsible to issue: Sales Admin Team | Executed via DocuSign Responsible: Sales Admin Team | Design team prepares sketch plan. Buildability reviewed by GURNER team. No dimensions on sketch plan. If dimensioned plans are provided, Gurner disclaimer must be added to plans. Responsible: Design Team + Customisations Manager | Sketch peer reviewed by architect and converted to CAD with updated marketing plan. Responsible: Customisations Manager | 01. Updated cost ranges provided by Quantity Surveyor (by Builder or QS) as per table 6.2 in Customisations Framework 02. Updated $20k consultant & Gurner allowance reported 03. All documentation initialled by client Produce letter: Customisations Manager Review of letter: Development Manager Responsible to issue: Sales Admin Team | Executed via DocuSign Responsible: Sales Admin Team | Design phase completed. Move to Phase 2 – COST. | Builder instructed to price the customisation and provide constructability input. This builder-pricing step is an internal workflow requirement and is not specified in clause 40.2 of this CoS. Responsible: Development Manager | Internal Gurner confirmation of cost build-up, margin alignment and final $20k soft costs allowance as per table 6.2 in Customisations Framework. Round final number to nearest $100. Responsible: Development Manager + Customisations Manager | Development team instructs QS to certify the cost impact of the agreed bespoke design changes. Responsible: Development Manager | Internal Gurner sign-off prior to issuing Deed of Variation. Gurner initials each page before issue. Responsible: Customisations Manager | Vendor drafts and issues Deed of Variation formally documenting agreed bespoke works, amended plans and specifications, and price adjustment. At the same time, the SA Invoice is also issued to the client. Responsible: Sales Admin Team | The purchaser must execute the Deed of Variation within 14 days after it is provided by the vendor. The contract is not varied unless and until the Deed of Variation is executed by both parties. If it is not executed, the property is delivered under the original Contract for Sale without the customisations. Responsible: Sales Admin Team | Builder instructed to proceed with variation and customisation. Responsible: Development Manager | Recommended latest date to submit planning modification application. Responsible: Development Manager | If required, the customisation is conditional on the vendor obtaining approval from the relevant Consent Authority under section 4.55 of the Environmental Planning and Assessment Act 1979 (NSW). If approval is not obtained, is unlikely to be obtained, or is subject to conditions unacceptable to the vendor, the vendor may rescind the contract. Responsible: Development Manager
[24 empty] | SC 67.2 / SC 68.2 | Framework | Framework | Framework | Framework | Framework | Framework | Framework | SC 68(c)(i)(B) – 150-day meeting only | Customisations Framework (not specified in CoS) | Framework | Customisations Framework; SC 68(c)(v) covers cost components only | Framework | SC 68(c)(iii) | SC 68(c)(iv) / SC 68(e)(i)–(ii) |  | Internal programme control | SC 68(f)
[24 empty] | 20 business days after COS Date | Immediately after brief | After Sketch Planning complete | After Sketch Plannign Complete | Immediately after brief | Immediately after Consultant review | During design period | After QS estimate | 150 Days After COS Date | Post design agreement | Prior to QS certification | After design agreement (~3 month non-contractural) | After QS certification | Issued after QS certification | 14 calendar days after DoV issued | DOV Execution Date | To be submitted upon DOV execution + 60 Days | Fixed sunset date
UNIT NUMBER | LOT NO. | NAME | Personal Address | AGENT | STATUS | 0. DATE ISSUED | 0. DATE EXCHANGED (Contract Date) | BASE PRICE | ALLOCATED UPGRADE BUDGET | PLAN OF SUB VERSION | CAR SPACE | ADDITIONAL CAR SPACE | MOTORBIKE | LEASE | SPEC SHEET | COLOUR SELECTION | AMALGAMATION | BESPOKE LOT | FRIENDS AND FAMILY | LIMITLESS DROP and TRACK IN PRICELIST | SAINT HAVEN | MEMBERSHIP TIER | CURRENT STATUS | 1.0 Written Brief Due / Design Briefing Session | 1.2 Sketch Plan Issued | 1.3 Letter #1 Issued: Cost Range and Layout Confirmed | 1.4 KEY MILESTONE: Layout and Cost Range Letter #1 Signed | 1.2 Buildability Review | 1.5 Sketch Layout Converted to CAD by Architect | 1.7 Letter #2 Issued: Updated Cost Range and Interiors Confirmed | 1.8 KEY MILESTONE: Interiors and Cost Range Letter #2 Signed | 1.9 Move to Phase 2 – COST | 2.1 Builder Pricing | 2.3 Internal Commercial Review | 2.2 QS Cost Certification | 3.1 Internal DOV Approval | 3.2 DoV and SA Invoice Issued to Client | 3.3 Client Executes DoV | 4.1 Instructed to Builder | 4.2 Planning / DA Modification Submission | 4.3 Modification Approval | Project Completion Deadline / Registratuion of Strata Plan with LRS (calculated) | SPECIAL CONDITIONS | BYLAWS VERSION | BESPOKE PLAN | CORRESPONDENCE | COST BORNE BY WHO | PRUCHASER COSTS (GURNER ESTIMATE/WT) | PURCHASER COSTS (HICKORY PRICE) | DEVELOPER COST (GURNER ESTIMATE/WT) | DEVELOPER COSTS (HICKORY PRICE) | OTHER DESIGN CHANGES | OTHER NOTES | BALL IN COURT | NEXT STEPS | COMMS LEAD
0701S | 48 | Virginia Nemeth |  | Apex | EXCHANGED |  | 2026-02-04 | 9600000 | TBC | 2025-09-09 | 1 | 0 | 0 | 0 | Diamond Collection | NONE | NO | NO | YES | YES | YES | PLATINUM | NA - No Bespoke Lot Clause | 2026-03-04 | Yes | [6 empty] | 2026-07-04 | [9 empty] | 2030-02-03 |  | ME_956752920_5 | 701S Plans | [7 empty] | Not a bespoke lot, however sketch plan has been sent. | DW | Setup in person design meeting, to finalize finshes and any design issued for signoff. (Deb to cooridnate appointment). Layout issued, awaiting comments | TBC
0702S | 49 | Virginia Nemeth |  | Apex | EXCHANGED |  | 2026-02-04 | 6400000 | TBC | 2025-09-09 | 0 | 0 | 1 | 0 | Diamond Collection | NONE | NO | NO | YES | YES | YES | PLATINUM | NA - No Bespoke Lot Clause | [8 empty] | 2026-07-04 | [9 empty] | 2030-02-03 |  | ME_956752920_5 | [8 empty] | Not a bespoke lot, do not offer | DW | no request issued, letter
0801S | 50 | Socorro Wescott |  | Apex | EXCHANGED |  | 2025-12-04 | 9700000 | TBC | 2025-09-09 | 1 | 0 | 0 | 0 | Diamond Collection | NONE | NO | YES | YES | NO | NO |  | 1.4 KEY MILESTONE: Layout and Cost Range Letter #1 Signed | 2026-01-01 | YES. | YES. | YES. | NO |  |  |  | 2026-05-03 |  |  | 2026-08-03 |  | 2026-08-03 | 2026-08-17 |  | 2026-10-16 | 2028-06-30 | 2030-12-04 | Deposit Bond ASC; Deferred Deposit ASC; Bespoke Lot ASC; Mod H not applicable; refer to hand sketches and emails for plan changes proposed | ME_956752920_5 | 801s & 802s Layout | Correspondence | Purchaser |  |  | REQUIRED |  | Wine fridge/cellar in storage cage (500-600 wine bottles) | Plan and wine cellar needs to be costed by WT | Purchaser | 24.03.26_WIM issued revised signoff letter with new layout. 16/03/26 - WM cofnirmed hydraulic riser relcoation acceotable with ADP 11/03/26_DW to email letter, cofirming layout | Deborah Wiltshire
0802S | 51 | Socorro Wescott |  | Apex | EXCHANGED |  | 2025-12-04 | 6500000 | TBC | 2025-09-09 | 1 | 0 | 0 | 0 | Diamond Collection | NONE | NO | YES | YES | NO | NO |  | 1.4 KEY MILESTONE: Layout and Cost Range Letter #1 Signed | 2026-01-01 | YES. | YES. | YES. | NO |  |  |  | 2026-05-03 |  |  | 2026-08-03 |  | 2026-08-03 | 2026-08-17 |  | 2026-10-16 | 2028-06-30 | 2030-12-04 | Deposit bond ASC; Deferred deposit ASC; Bespoke Lot ASC; Mod H not applicable; refer to hand sketches and emails for plan changes proposed | ME_956752920_5 | 801s & 802s Layout |  | Purchaser |  |  | REQUIRED |  | Wine fridge/cellar in storage cage (500-600 wine bottles) | Plan and wine cellar needs to be costed by WT | Purchaser | 24.03.26_WIM issued revised signoff letter with new layout. 16/03/26 - WM cofnirmed hydraulic riser relcoation acceotable with ADP 11/03/26_DW to email letter, cofirming layout | Deborah Wiltshire
0901S | 52 | John Corollo |  | APEX | EXCHANGED |  | 2025-10-28 | 9800000 | TBC | 2025-09-20 | 1 | 0 | 0 | 0 | Diamond Collection | NONE | NO | YES | YES | NO | NO |  | 1.4 KEY MILESTONE: Layout and Cost Range Letter #1 Signed | 2025-11-25 | YES. | YES. | YES. | NO |  |  |  | 2026-03-27 |  |  | 2026-06-27 |  | 2026-06-27 | 2026-07-11 |  | 2026-09-09 | 2026-10-28 | 2030-10-28 | Family & Friends ASC Bespoke Lot ASC | ME_956752920_5 | 901S Plans | 901s_Layout Signoff Letter_13.08.26_ Solus Places.pdf | Purchaser | [5 empty] | Plan needs to be costed by WT POS should be 9/9/25 | WM | 27.03.26 WM to Draft Letter Setup in person design meeting, to finalize finshes and any design issued for signoff. (Deb to cooridnate appointment). Forward correspondence with purchaser, confirm layout | Deborah Wiltshire. Deb
1901N | 35 | Peter Ping Xie and Xiao Ling Shen Wholms Pty Ltd |  | APEX | EXCHANGED |  | 2025-09-29 | 21950000 | 1000000 | 2025-09-09 | 1 | 1 | 0 | 0 | Penthouse Collection | NONE | NO | NO | YES | YES | YES | ULTIMATE | NA - No Bespoke Lot Clause | 2025-10-27 | YES. |  |  | NO |  |  |  | 2026-02-26 |  |  | 2026-05-26 |  | 2026-05-26 | 2026-06-09 |  | 2026-08-08 | 2028-06-30 | 2030-09-29 | Limitless ASC (Side Letter) Saint Haven Membership ASC (Side Letter) | ME_956752920_5 | 1901N Plans |  | GURNER |  |  | REQUIRED |  | Wellness terrace upgrades - refer to plan | Additional car space given for a total of 2 car spaces Cost of upgrades to terrace are included within Contract Price (cost uplift not to be paid for by purchaser)
1001N |  | Domenico Cece & Teresa Maria Cece |  | Inspired Wealth | ISSUED | [17 empty] | 1.1 Sketch Plan Issued |  | YES |  |  | NO |  |  |  | 1900-05-29 | [12 empty] | I |  |  |  |  | REQUIRED |  |  | Revised layout issued, redsign to be priced and included in Contract. ADAPTABLE LOT - needs to be considered in Bespoke lot design | DW | 25.03- Layout signoff letter issued to DW
1001S |  | Pierre Bouantoun |  | Inspired Wealth | ISSUED | [22 empty] | NO |  |  |  | 1900-05-29
1002S | 55 | Michael Dakhoul & Houda Dakhoul |  | The Agency | EXCHANGED |  | 2025-12-24 | 6550000 | TBC | 2025-09-09 | 1 | 0 | 0 | 0 | Diamond Collection | NONE | NO | NO | NO | NO | NO |  | NA - No Bespoke Lot Clause | [8 empty] | 2026-05-23 | [9 empty] | 24 Dec 2030 | Deposit Bond ASC; Deferred Deposit ASC | ME_956752920_5 | [9 empty] | DW | Deb to liase with The Agency to setup design meet. Follow up with Purchaser on any design changes needed. Connect with Deb
1202S | 59 | Tom Lin |  | The Agency | EXCHANGED |  | 2025-11-06 | 8250000 | 350000 | 2025-09-20 | 1 | 0 | 0 | 0 | Diamond Collection | NONE | NO | YES | NO | NO | NO |  | 1.2 Buildability Review | 2025-12-04 | YES. |  |  | NO |  |  |  | 2026-04-05 |  |  | 2026-07-05 |  | 2026-07-05 | 2026-07-19 |  | 2026-09-17 | 2028-06-30 | 06 Nov 2030 | Bespoke Lot ASC | ME_956752920_5 | 1202S Plans | Customisation Letter | Purchaser | [5 empty] | Plan has been costed by WT POS should be 9/9/25 Should include the Mod H back up plan but does not. Changes marked up,Gurner Design to update drawing. Include larger sink but maintain island bench size. Refer page 6 of COS. Design session remotely due to overseas buyer. (C) enlarged ensuite to accommodate round bath; (D) inclusion of project vault off newly formed dressing room; (E) butlers kitchen being opened to living area to accommodate onyx bar; and incorporation of onyx bar into study area on entry. | DW | 09/03/26 WM issued draft letter to Deb. Once signed off WM to get pricing/FJC to document | Deb
1402N | 26 | Michael Bourke |  | The Agency | EXCHANGED |  | 2025-10-27 | 8750000 | 0 | 2025-09-20 | 1 | 0 | 0 | 0 | Diamond Collection | COOL | NO | NO | NO | NO | NO |  | NA - No Bespoke Lot Clause | [8 empty] | 2026-03-26 | [9 empty] | 27 Oct 2030 |  | ME_956752920_5 | NA | [7 empty] | No incentives POS should be 9/9/25 Should include the Mod H back up plan but does not | DW | 11/3/26 Deb to follow up with Apex on Status of Internal Design. 11/03/26 FJC to develop terrace design and coordinate into documentation for Pricing. | Deb
1701S | 68 | Hani Sedaris |  | The Agency | EXCHANGED |  | 2025-09-22 | 9450000 | TBC | 2025-09-09 | 1 | 0 | 0 | 0 | Diamond Collection | COOL | NO | YES | NO | NO | NO |  | 1.2 Buildability Review | 2025-10-20 | NO |  |  | NO |  |  |  | 2026-02-19 |  |  | 2026-05-19 |  | 2026-05-19 | 2026-06-02 |  | 2026-08-01 | 2028-06-30 |  | Bespoke Lot ASC | ME_956752920_5 | No plan yet |  | Purchaser | [5 empty] | Bespoke lot process to be done Deposit bond noted in Salesforce | DW | Deb to send email to agent confiming the current status of the amalgamations. | Deb
1901/1902S | 72 & 73 | Marco Hara |  | The Agency | EXCHANGED |  | 2025-10-10 | 19300000 | TBC | 2025-09-20 | 1 | 0 | 0 | 0 | Penthouse Collection | COOL | YES | YES | YES | NO | NO |  | 1.2 Buildability Review | 2025-11-07 | YES. |  |  | NO |  |  |  | 2026-03-09 |  |  | 2026-06-09 |  | 2026-06-09 | 2026-06-23 |  | 2026-08-22 | 2028-06-30 | 10 Oct 2030 | Family & Friends ASC Consolidation of Lots (with no plan attached) ASC | ME_956752920_5 | 1901S & 1902S Plans | Correspondence | Finishes - GURNER Amalgamation - Purchaser | 37834 |  | 175979 |  |  | Plan needs to be costed by WT Upgrade from Diamond to PH collection (for free - TG offer) POS should be 9/9/25 | DW | Deb to send email to agent confiming the current status of the amalgamations.
2001/2002S | 74 & 75 | Property Holdings No 2 Pty Ltd |  | The Agency | EXCHANGED |  | 2025-10-15 | 19600000 | TBC | 2025-09-20 | 1 | 0 | 0 | 0 | Penthouse Collection | COOL | YES | YES | YES | NO | NO |  | 1.3 Letter #1 Issued: Cost Range and Layout Confirmed | 2025-11-12 | YES. |  |  | NO |  |  |  | 2026-03-14 |  |  | 2026-06-14 |  | 2026-06-14 | 2026-06-28 |  | 2026-08-27 | 2028-06-30 | 15 Oct 2030 | Family & Friends ASC Consolidation of Lots (with no plan attached) ASC | ME_956752920_5 | 2001S & 2002S Plans |  | Finishes - GURNER Amalgamation - Purchaser | 37834 |  | 175979 |  |  | Upgrade from Diamond to PH collection (for free - TG offer) Bespoke lot process to be done POS should be 9/9/25 | GD | 09/03/26 - Revised layout issued to client, awaiting response. | Deb
2101/2102S | 76 & 77 | Jack Davis Rice |  | The Agency | EXCHANGED |  | 2025-10-11 | 19900000 | TBC | 2025-09-20 | 1 | 0 | 0 | 0 | Penthouse Collection | COOL | YES | YES | YES | YES | YES | ULTIMATE | 1.2 Buildability Review | 2025-11-07 | YES. |  |  | NO |  |  |  | 2026-03-10 |  |  | 2026-06-10 |  | 2026-06-10 | 2026-06-24 |  | 2026-08-23 | 2028-06-30 | 11 Oct 2030 | Family & Friends ASC Consolidation of Lots (with no plan attached) ASC | ME_956752920_5 | 2101S & 2102S Plans |  | Finishes - GURNER Amalgamation - Purchaser | 37834 |  | 175979 |  |  | Upgrade from Diamond to PH collection (for free - TG offer) Bespoke lot process to be done POS should be 9/9/25 | DW | 13/03/26 DW to review budget estimate with Client, provided by WT.
2101N | 37 | Denise Azzi (Charlie Ayoub) |  | The Agency | EXCHANGED |  | 2026-02-19 | 39000000 | TBC | 2025-11-10 | 4 | 0 | 0 | 0 | Penthouse (custom) | NONE | NO | YES | NO | NO | NO |  | 1.2 Buildability Review | 2026-03-19 | YES |  |  | NO |  |  |  | 2026-07-19 |  |  | 2026-10-19 |  | 2026-10-19 | 2026-11-02 |  |  | 2028-06-30 | 19 Feb 2031 | Renders ASC, Deferred Deposit ASC, Bespoke Lot ASC, Deposit Bond ASC, Draft Strata Plan ASC | ME_956752920_5 | 2101N Plans |  | TBC |  |  | REQUIRED |  |  | Explore elevator options, purchaser cost
1501S/1502S |  | Harminder Singh |  | The Agency | ISSUED | [11 empty] | No intention- interconnecting door | [10 empty] | NO |  |  |  | 1900-05-29 | [20 empty] | At this stage, keep them as indiviual residences. | GD | Preparing initial sketch, in response to their CAD file
1601S/1602S |  | Sophia Chhe |  | The Agency | ISSUED | [11 empty] | Intention | [10 empty] | NO |  |  |  | 1900-05-29 | [20 empty] | Issued as amalgmation |  |  | Deb
902S | 53 | Edward Dakhoul & Norma Rose Dakhoul |  | The Agency | EXCHANGED |  | 2026-03-02 | 6350000 | 0 | 2025-09-09 | 1 | 0 | 0 | 0 | Diamond Collection | COOL | NO | NO | NO | NO | NO |  | NA - No Bespoke Lot Clause | [8 empty] | 2026-07-30 | [9 empty] | 02 Mar 2031 | Deferred Deposit ASC Deposit Bond ASC | ME_956752920_5 | NA | [7 empty] | Awaiting exchnage prior to design sessions Damon: not a bespoke lot. Do not offer | DW | Deb to find out from Evan latest design status | Evan
1801/1802S | 70/71 | Jia Zhou | 6903/1A Barangaroo Avenue, BARANGAROO, NSW 2000 | The Agency | EXCHANGED |  | 2026-05-14 | 19000000 | 0 | 2025-09-09 | 1 | 1 | 0 | 0 | Diamond Collection | NONE | YES | YES | NO | NO | YES | ULTIMATE | 1.2 Sketch Plan Issued |  | YES. | [6 empty] | 2026-10-11 | [19 empty] | Free V-zug refresh butler, fireplace, PHC walk in robe Chevron floorboards mentioned but not in contract?? |  |  |  | Evan
2501S | 80 | Damian Hanna | 38 Northland Road, Bellevue Hill, NSW, 2023 | The Agency | EXCHANGED |  | 2026-03-02 | 28500000 | TBC | 2025-09-09 | 2 | 0 | 0 | 0 | Penthouse Collection | NONE | NO | YES | NO | NO | NO |  | 1.3 Letter #1 Issued: Cost Range and Layout Confirmed | 2026-03-30 | YES. | YES. | [5 empty] | 2026-07-30 |  |  | 2026-10-30 |  | 2026-10-30 | 2026-11-13 |  | 2027-01-12 | 2028-06-30 | 02 Mar 2031 | Bespoke Lot ASC Deferred Deposit ASC | ME_956752920_5 |  |  | Purchaser |  |  |  |  | Bespoke Lot ASC makes reference to ‘pool table’ render – purchaser may elect to customise the Property to incl lounge area and wine display with similar look and feel. Render not in contract. | This is an “adaptable” unit which will limit the bespoke lot customisation process somewhat as it must maintain certain corridor, door widths etc. Billiard table not Pool Table Ensure the checkerboard pattern in lift lobby is included and not carpet | 1 | 11/03/26 DW to contact the Agency and cooridnate a Gurner Design Session. | Deb
1102S | 57 | Hye Young (Hayley) Han | 27 Jenkins Street, COLLAROY, NSW 2097 | The Agency | EXCHANGED |  | 2026-05-07 | 8100000 | 0 | 2025-09-09 | 0 | 0 | 1 | 0 | Diamond Collection | COOL | NO | NO | NO | NO | YES | ULTIMATE | [9 empty] | 2026-10-04
602S | 47 | Shaoping Liang | 17 Seaforth Crescent, SEAFORTH, NSW 2092 | The Agency | EXCHANGED |  | 2026-05-14 | 6300000 | 0 | 2025-09-09 | 0 | 0 | 0 | 1 | Diamond Collection | WARM | NO | NO | NO | NO | YES | ULTIMATE | [9 empty] | 2026-10-11
502S | 45 | Nathan Nassim Jammal | 12 Pile Street, GLADESVILLE, NSW 2111 | The Agency | EXCHANGED |  | 2026-05-21 | 6000000 | 0 | 2025-09-09 | 0 | 0 | 0 | 1 | Diamond Collection | COOL | NO | NO | NO | NO | NO | [10 empty] | 2026-10-18 | [19 empty] | Free upgrade: timber floorboards to all bedrooms
1702S | [7 empty] | 9250000 | 0 | 2025-09-09 | 1 | 0 | 0 | 0 | Diamond Collection | WARM | NO | NO | NO | NO | NO
Formulas:
COS = EDATE([COS],3)
COS = [COS]
Gurner Framework = [COS]+60
Note on AA8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Why?
Note on S10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Has asked to amalgamate for land tax reasons
Note on S11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Has asked to amalgamate for land tax reasons
Note on B13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Contracts Team don’t have the contract for 1901N. Do we need to ask Minters for it?
Note on K13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Extra 1x Carspace
Note on R13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Need to check this.
Note on T13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Need to check this - however customisations to the terrace have been agreed
Note on K17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: WT estimate 21 Oct 2025
Note on Q20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Free upgrade to PH Collection offered by TG
Note on Q21: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Free upgrade to PH Collection offered by TG
Note on Q22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Free upgrade to PH Collection offered by TG
Note on V22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Email from Sean Carey 04/03 saying this was instructed by Tim
Note on W22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Email from Sean Carey 04/03 saying this was instructed by Tim

## Design Fees
| Total | G1890DH2797 | G1890DH2891 | Invoice | Invoice | Invoice | Invoice | Invoice | Invoice | Invoice | Invoice | Invoice | Invoice | Invoice | Invoice | Invoice | Invoice | Invoice | Invoice
|  | 2026-04-09 | 2026-05-31 | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date
1901N | 5176.25 |  | 5176.25
2101N | 26461.25 | 19052.5 | 7408.75
801S | 3056.25 |  | 3056.25
802S | 2197.5 |  | 2197.5
1801S | 2861.25 |  | 2861.25

## Sunset Table
Apartment | Contract Date | Clause Reference | Clause Description | Clause Type | True Sunset Basis | Calculated Sunset
702S | 03 Feb 2026 | Cl 54 (amended) | replace 60 months with 48 months | Global amendment | 48 months | 03 Feb 2030
801S | 04 Dec 2025 | Cl 33.1 | Completion date amended only | Default | 60 months | 04 Dec 2030
802S | 04 Dec 2025 | Cl 33.1 | Completion date amended only | Default | 60 months | 04 Dec 2030
901S | 28 Oct 2025 | Cl 33.1 | MC Sunset = 12 months | Clause-specific | 60 months | 28 Oct 2030
902S | 02 Mar 2026 | - | No variation | Default | 60 months | 02 Mar 2031
1002S | 24 Dec 2025 | - | No variation | Default | 60 months | 24 Dec 2030
1202S | 06 Nov 2025 | Cl 33.1 | MC Sunset = 30 Jun 2027 | Clause-specific | 60 months | 06 Nov 2030
1402N | 27 Oct 2025 | Cl 33.1 | MCSD amended to 30 Jun 2027 | Clause-specific | 60 months | 27 Oct 2030
1901N | 29 Sep 2025 | - | No variation | Default | 60 months | 29 Sep 2030
2101N | 2026-02-19 | SC37 | Sunset = 18 months (SC only) | Clause-specific | 60 months | 19 Feb 2031
2501S | 02 Mar 2026 | SC37 | Sunset = 24 months (SC only) | Clause-specific | 60 months | 02 Mar 2031
1901S & 1902S | 10 Oct 2025 | Cl 54 | Standard sunset clause | Default | 60 months | 10 Oct 2030
2001S & 2002S | 15 Oct 2025 | Cl 54 | Standard sunset clause | Default | 60 months | 15 Oct 2030
2101S & 2102S | 11 Oct 2025 | Cl 54 | Standard sunset clause | Default | 60 months | 11 Oct 2030